## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US01 | Upload CV | As a TA Applicant, I want to upload my CV in PDF format, so that the MO can review my qualifications. | Must +1 | 1 +1 | 1. Accepts PDF/TXT files. 2. Success message appears. 3. Data saved in text file.+2 | 3 | Core hiring function. | 2026-03-14 | 2026-03-22
US02 | Post Job | As a Module Organiser (MO), I want to post a new TA job, so that I can find assistants for my module.+1 | Must +1 | 1 +1 | 1. Fields: Module Name, Job Description. 2. Job visible in list immediately. | 5 | Required for basic workflow. | 2026-03-14 | 2026-03-22
US03 | Apply for Job | As a TA Applicant, I want to apply for available jobs, so that I can be considered for the role. | Must +1 | 1 +1 | 1. User can click "Apply". 2. System records application details in text file. | 3 | Essential for recruitment. | 2026-03-14 | 2026-03-22
US04 | Skill Matching | As an MO, I want to match applicant skills with job requirements, so that I can select the best candidate. | Could +1 | 3 +1 | 1. Compare CV text with job keywords. 2. Use AI to provide match score. | 8 | AI-powered feature. | 2026-04-14 | 2026-04-26